## Capital Funding Recommendations
Recommendations | NAO comment or DfE Response to the recommendation | DfE implementation status | Further NAO comment
Recommendations from NAO Report 2017: Capital Funding for Schools
b The Department should evaluate the quality of the buildings provided through its main capital programmes to allow it to assess cost-effectiveness and identify good practice | NAO comment: See Department documents fieldwork URNs 6, 7 and 8 for a set of outputs that include lessons learnt from PSBP
c The Department should continue to improve its understanding of the condition of the school estate and consider how it can get more value out of the next property data survey. For example, it should compare the findings with the previous survey and analyse the data in greater depth to understand patterns of condition need. | NAO comment: While the process is less than perfect, CDC1 (and CDC2 in due course) provides DfE with significantly enhanced intelligence on the condition of the estate. In this sense, DfE has clearly complied with the spirit of the recommendation.
d The Department should work more closely with local authorities to understand and meet need in local areas. For example, it should share information earlier on the condition of the school estate and the need for places, and improve how it liaises with local authorities about the location of free schools | NAO comment: What do we know about this?
e The Department should make the system work better by: • setting out clearly the responsibilities and accountabilities of local authorities and academy trusts for managing the school estate; • providing incentives for local authorities and academy trusts to maintain school buildings well, including by undertaking important but not necessarily urgent maintenance work; and • supporting local authorities and academy trusts to strengthen their management of land and buildings. | NAO comment: DfE has made/is making progress here, through actions such as: creating GEMS, regularly issuing newsletters; launching the Capital Advisers' Porgramme (CAP). IT is also developing the Estates Management Competency Framework.
Recommendations from the PAC Report | Response to the Recommendation - Treasury Minutes October 2017 | Treasury Minutes Progress Report: July 2018
Recommendation 5: The Department should set out a plan by December 2017 for how it will fill gaps in its knowledge about the school estate in areas not covered by the property data survey. Specifically it needs to understand the prevalence, condition and management of asbestos, and know more about the general suitability and safety of school buildings. | 5.1 The Government agrees with the Committee's recommendation. Recommendation Implemented 5.2 The Department has developed a plan to improve its information about the school estate, building on the Property Data Survey (PDS), and is taking this plan forward. 5.3 The Department's role is to support academy trusts, local authorities and VA bodies, including church dioceses, in carrying out their responsibilities to maintain and ensure the safety and suitability of school buildings. In line with this role, the Department's Condition Data Collection (CDC) programme is expanding and improving on the work of PDS, collecting condition data from every school in England by September 2019. It will contribute to the Department's knowledge of the estate by: - Providing a current assessment of the condition of schools - revising the assessment of backlog maintenance cost -highlighting the overall change in school condition since PDS; and - collecting data on statutory maintenance management, including in relation to asbestos 5.4 In addition, the Department is further developing its knowledge of the school estate by using data from DC and other school engagements to identify specific areas of weakness and provide targeted remedical advice and support to schools; building on Managing Asbestos in your School guidance and work carried out to assess compliance with asbestos regulations by developing an assurance mechanism to secure information about compliance from responsible bodies; and sharing insights gathered through investigation of particular condition issues with all responsible bodies.
Recommendation 6: The Department should use information, including from the property data survey, to develop a robust approach for holding local authorities and academy trusts to account for maintaining their school buildings, including how it will intervene if they are not doing so effectively. It should also assess whether schools can afford the level of maintenance necessary given the real-terms reductions in funding per pupil | 6.1 The Government agrees with the Committee's recommendation. Target implementation date: April 2018 6.2 Under the national funding formula, there will be an additional £1.3 billion for schools and high needs across 2018-19 and 2019-20, on top of existing spending plans. This means that core funding for schools will rise from almost £41 billion 2017-18 to £42.4billion in 2018-19. In 2019-20, this will rise again to £43.5 billion. This represents an increase of £2.6 billion, and means funding per pupil will now be maintained in real terms for the remaining two years of this Spending Review. 6.3 On capital funding, the Government is providing £1.4 billion of condition funding directly to the sector in 2017-18, to enable schools, local authorities and academy trusts to carry out essential ongoing and preventive maintenance, repairs and refurbishments 6.4 To prevent expensive maintenance issues in the future, it is essential this funding is spent wisely. As such, the Department is developing new data sources that will enable it to monitor whether the funding provided for school maintenance and improvement is being used efficiently. Data on the condition of the school estate will be analysed with data collected on schools' actual spending on maintenance and improvement in order to understand and compare spending patterns and changes in condition. This, in turn, will allow the Department to develop better metrics and benchmarks to compare performance, enabling it to identify where and when it needs to intervene to challenge and support improvement. 6.5 The Department will report back in April 2018 on the improvements it has made to monitoring performance and holding responsible bodies to account for maintaining their school buildings. | Recommendation Implemented | Are we convinced about: "Data on the condition of the school estate will be analysed with data collected on schools' actual spending on maintenance and improvement in order to understand and compare spending patterns and changes in condition. This, in turn, will allow the Department to develop better metrics and benchmarks to compare performance, enabling it to identify where and when it needs to intervene to challenge and support improvement." ?
Recommendation 7 (part one): The Department should report back to us by the end of December 2017 on the quality and suitability of new school buildings provided under the Priority School Building Programme and Free Schools Programme, including the temporary accommodation that is being used for some free schools. | Recommendation 7A: 7.1 The Government agrees with the Committee's recommendation Target implementation date: December 2017 7.2 The Department has already implemented steps to ensure new school buildings meet design standards and are suitable for the provision of high quality education 7.3 The Department is focused on delivering schools under the Priority School Building Programme (PSBP) and free schools programme that support educational attainment, are simple to operate and have low ongoing running costs. The Department's design standards and specifications ensure that new buildings keep cool in summer and warm in winter, have sufficient space and are fitted with windows that are designed to maximise natural light. In delivering new buildings, the Department works closely with schools to ensure that the design is suitable for their needs. It has developed baselines designs for schools which demonstrate how standards and specifications can be met, providing a robust starting point for the design of all projects. 7.4 Standards and specifications are reviewed regularly to reflect changing requirements and lessons learnt. The current specifications was published in 2013 and included considerable changes in response to issues identified using Post Occupancy Evaluation (POE). A new version, incorporating lessons learnt from school building programmes, will apply from November 2017. The ongoing POE includes both stakeholder surveys and building performance evaluation to ensure that buildings are performing as expected. As part of the overall POE strategy, the ESFA will shortly be commencing targeted end user engagement. 7.5 Free schools open in temporary accommodation either because the permanent site is not completed or has not yet been acquired. The Department evaluates the viability of any proposed temporary solution and ensures that all temporary accommodation is safe and suitable for educational purposes. 7.6 The Department will report back on the ongoing POE in the January 2018 Treasury Minute Progress Report. | Recommendation Implemented | NAO comment: See Department documents fieldwork URNs 6, 7 and 8 for a set of outputs that include lessons learnt from PSBP. Teach-in 7, on SRP delivery and performance, produced the following: "DfE also runs a very large post-project evaluation effort, looking at building quality, performance, etc, in an attempt to get better VFM in future projects. The outputs from these post-project evaluation exercises are not published, because they’re intended for internal consumption. But DfE are happy to share them with us. In recent years, standardisation of approaches has been the focus – i.e. doing the same things on a repeated basis. Even SEND schools were standardised, which is something that wasn’t generally thought possible. In 2018, DfE brought together all specifications into one standard specification – so everyone gets consistency of outcomes. DfE is looking to produce simple, straightforward buildings, taking a “fabric first” approach."